## Generator deployments
Job Ref | Location Description | Post Code | OS Grid Ref | Easting | Northing | Latitude | Longitude | Gen Size (kVA) | dB(A) @ 7m | Hours | Planned Start | Duration (days) | Reason | Requested By
GEN-001 | Hoole Road 11kV substation, Chester | CH2 3ND | [5 empty] | 500 |  | 24h | 2026-11-03 | 3 | Planned outage - 11kV switchgear replacement | Network Ops Cheshire
GEN-002 | Beaufort Road, Birkenhead | CH41 1HQ | [5 empty] | 800 | 72 | Night only | 2026-11-10 | 2 | Overnight LV board change | Network Ops Wirral
GEN-003 | Llannerch water treatment works feed | LL17 0BB | [5 empty] | 250 |  | 24h | 2026-11-17 | 5 | Resilience cover for critical customer | Network Ops North Wales
GEN-004 | Nanhoron, Llyn peninsula |  | SH 2643 3099 |  |  |  |  | 100 |  | 24h | 2026-11-24 | 7 | 11kV overhead line rebuild | Network Ops North Wales
GEN-005 | Caernarfon Road, Bangor |  |  | 256327 | 369890 |  |  | 400 |  | Daytime | 2026-12-01 | 1 | Pole-mounted transformer replacement | Network Ops North Wales
GEN-006 | Wrexham town centre substation |  | SJ 334 503 |  |  |  |  | 500 |  | 24h | 2026-12-02 | 4 | Primary transformer maintenance | Network Ops Wrexham
GEN-007 | Llangollen valley pole-mounted transformer |  | SJ 215 420 |  |  |  |  | 60 |  | Daytime | 2026-12-08 | 1 | Pole replacement | Network Ops Wrexham
GEN-008 | Denbigh Moors farm supply |  | SH 950 560 |  |  |  |  | 200 |  | Daytime | 2026-12-09 | 2 | Storm damage repair | Network Ops North Wales
GEN-009 | Llangefni, Anglesey |  | SH 458 757 |  |  |  |  | 150 | 66 | 24h | 2027-01-12 | 3 | Cable fault - temporary supply | Network Ops Anglesey
GEN-010 | Pyms Lane industrial estate, Crewe | CW1 3PL | [5 empty] | 1000 | 75 | 24h | 2027-01-18 | 10 | HV customer supply during cable diversion | Network Ops Cheshire
GEN-011 | School Lane, Warmingham |  |  | 371011 | 361341 |  |  | 250 |  | Night only | 2027-01-25 | 2 | Rural ring main unit replacement | Network Ops Cheshire
GEN-012 | Neston distribution centre | CH64 3TS | [5 empty] | 150 |  | 24h | 2027-02-01 | 2 | Substation earthing upgrade | Network Ops Wirral
GEN-013 | Moss End Way, Kirkby |  |  |  |  | 53.4874 | -2.8466 | 630 |  | 24h | 2027-02-08 | 3 | Unit substation replacement | Network Ops Merseyside
GEN-014 | Trefarclawdd, near Oswestry | SY10 9DE | [5 empty] | 100 | 64 | 24h | 2027-02-15 | 2 | 11kV pole-mounted auto-recloser change | Network Ops Wrexham
GEN-015 | Rhyl promenade kiosk |  | TBC |  |  |  |  | 200 |  | 24h | 2027-02-22 | 1 | Location still to be confirmed | Network Ops North Wales
GEN-016 | Depot test unit (wrong region) |  | NS 590 650 |  |  |  |  | 60 |  | Daytime | 2027-03-01 | 1 | Shows a site outside the covered area | Network Ops

## Notes
Example input for the generator site screening tool. All sites are made up.
Locations deliberately use different formats (postcode, OS grid reference, easting/northing, latitude/longitude) to show the tool reads each row as it is.
GEN-015 has no usable location and GEN-016 is outside the area covered; both appear on the tool's 'could not be screened' list.
Columns the tool does not use (Planned Start, Duration, Reason, Requested By) are ignored.
Postcodes are real public postcodes in the SP Manweb area, taken from the Renewable Energy Planning Database.